## Sheet1
1430 Del Paso, the ice rink
	Date	Permit Number	Record Type	Description	Status
	12/28/2010	COM-1013107	Building/Commercial/Repair-Maintenance/With Plans	PHASED FROM COM-1013101 ---INSTALL ENTRYWAYS, DASH	Finaled
	12/28/2010	COM-1013101	Building/Commercial/Repair-Maintenance/With Plans	TEMPORARY AND INTERIM IMPROVEMENTS TO ARSON DAMAGE	Finaled
	11/10/2010	COM-1011501	Building/Commercial/Minor/No Plans	Minor emergency electrical repair.	Finaled
	04/09/2010	COM-1003277	Building/Commercial/Housing Dept Permit/With Plans	10-008136 ---Fire Damage--Interior demo.	Finaled

0 Lochbrae		Note: This was the address before we had it all parcelized and addressed. This was required for permit on 1427 Lochbrae below
	Date	Permit Number	Record Type	Description	Status
	08/09/2011	COM-1107894	Commercial Repair-Maintenance	Repair interior dry rot at shed & electrical work	Expired Application
				This was the project to complete the dry rot repair that we started on the rink storage shed.

1427 Lochbrae Rd, the rink storage shed
	Date	Permit Number	Record Type	Description	Status
	12/29/2010	COM-1013125	Building/Commercial/Minor/No Plans	Service panel change out on Ice Rink property	Expired Permit
				We got the temp power approved but didn't finish this permit. The City wanted us to file plans for all the interior electrical. We never got this done.